## MP_JoblistItems
|  | 1 | Urgent
Joblist |  | 2 | Main work
AFTER VAL21T05 |  | 3 | Background work
|  | 4 | Awaiting Info
|  | 5 | Not to be worked on
Description | Who | Priority | Complete Target | Notes | Remove from list
Re-Align VI-grade model for damper on rig simulations | MP | 1 | 100%
First simulations with pre-T05 and post-T05 configuration | MP | 1 | 75%
Export data for Michelin | MP | 2 | 100%
Operating limits after VAL21T05 | MP | 2 | 100% | Maybe Francesco can help.. No, he did not help… NO check on the engine since no more at Podium
Brake report after VAL21T05 | MP | 2 | 100%
Set down of the car | MP | 4 | 0% | Can I ask to mechanics to do it before dismounting the car? --> Clearly no more possible…
Data Analysis report after VAL21T05 | MP | 2 | 95% | Refine Fuel consumption part, clarify brake power and decide what to show in sims comparison
Go On with WinTAX Layout for Aragon | MP | 2 | 30% | Investigate with Max how to work around TelemetrryVsLogger channels
Send to Drivers best lap comparison | MP | 3 | 100% | Did the best about alignment considering very different damping setups and beacon fail in RB stint
Try to make rear suspension geometry to work on Canopy | MP | 3 | 0%
Fuel consumption report page | MP | 2 | 100%
Build a tool to forecast influence of clicks on damper characteristics | MP | 3 | 0%
To FIA presentation about refuel time needed | MP,SR | 1 | 60% | Waiting for infos about last "bancage" session to update simulations